## Slide 1: Emerging Frontiers of Science of Information
Management Objectives,
Structure, and Operation

## Slide 2: Management Objectives
“To provide mechanisms for synergistic research and development of foundational principles, methods, and applications of post-Shannon information theory.
To educate and train the next generation of information sciences practitioners
To deeply engage students, researchers, and affiliated personnel from underrepresented groups in all aspects of the project.
To facilitate seamless transfer of knowledge to the broader academic and commercial world.”

## Slide 3: Management Goals: Research and Development
Coordinate all projects to leverage research efforts across the Center
Constitute mechanisms for rewarding synergistic development, identifying promising research directions ,and terminating stagnant projects in a timely manner, and allocate resources accordingly.
Engage the broader scientific community to evolve our shared vision of information sciences
Involve the applications community to build up novel methods, formalisms, and products of the research and development plan
Develop an industrial outreach plan focused on timely dissemination of results to industry and enabling them to influence research and development efforts

## Slide 4: Management Goals: Education and Training
Engage students from K-12 to post-doctoral researchers in the emerging concepts associated with information science
Develop a coherent educational and diversity plan across various project sites focused on research involvement at all level
Develop a novel curriculum across project sites, integrating theory and applications of information science
Constitute mechanisms for initiating/ evaluating educational programs and their impact, as well as providing guidance and appropriate resources.
Train educators to maximize impact
Develop widely accessible instructional resources

## Slide 5: Management Goals: Diversity and Outreach
Leverage tremendous interdisciplinary opportunities in engaging underrepresented groups in all aspects of research and education.
Develop processes for effectively engaging our partners to leverage their talent pool and train the next generation of researchers.
Develop programs for outreach to untapped resources, including schools, community colleges, and industry.
Notes: This could be split into two slides, one on diversity/outreach, and one on knowledge transfer, if combining makes these areas appear diminished in terms of goals.

## Slide 6: Management Goals: Knowledge Transfer
Constitute processes for timely and broad dissemination of project outcomes
Assimilate promising research avenues and applications from the broader community (industry, labs, as well as academia).
Enable the broader community to influence Center activities and to engage with the Center in mutually beneficial ways.
Notes: This could be merged with the slide on diversity/outreach to streamline, although combining may make these areas appear diminished in terms of goals.

## Slide 7
Vice President for Research
Purdue University
Executive Committee
External Advisory Board
Technical Director
Szpankowski
Managing Director
Kotterman*
Technical Thrusts
Education and Human Resources Development
Knowledge Transfer
Diversity and Outreach
Management Structure
Internal Management
Committee
Structural goal: coordinate center activities, ensure availability of resources,
maintain accountability, and ensure achievement of all project goals

## Slide 8
Vice President for Research
Purdue University
Executive Committee
External Advisory Board
Technical Director
Szpankowski
Managing Director
Kotterman*
Technical Thrusts
Education and Human Resources Development
Knowledge Transfer
Diversity and Outreach
Management Structure
Internal Management
Committee
Vice President for Research
Purdue University
Responsible for administrative oversight of the project
Provides timely access to university facilities and resources
Provides a liaison to student programs and academic units
Ensures accountability to the National Science Foundation

## Slide 9
Vice President for Research
Purdue University
Executive Committee
External Advisory Board
Technical Director
Szpankowski
Managing Director
Kotterman*
Technical Thrusts
Education and Human Resources Development
Knowledge Transfer
Diversity and Outreach
Management Structure
Internal Management
Committee
Technical Director: Establishes high-level goals and strategic directions; manages all center activities; coordinates and executes management decisions and advice from executive and advisory committees; point of contact with NSF
Managing Director: Coordinates day-to-day center activities (100% effort)
Technical Director
Szpankowski
Managing Director
Kotterman*

## Slide 10
Vice President for Research
Purdue University
Executive Committee
External Advisory Board
Technical Director
Szpankowski
Managing Director
Kotterman*
Technical Thrusts
Education and Human Resources Development
Knowledge Transfer
Diversity and Outreach
Management Structure
Internal Management
Committee
Executive Committee: Guides progress and vision; evaluates projects; coordinates efforts of different groups; strategizes to maximize Center’s impact.
Executive Committee

## Slide 11
Vice President for Research
Purdue University
Executive Committee
External Advisory Board
Technical Director
Szpankowski
Managing Director
Kotterman*
Technical Thrusts
Education and Human Resources Development
Knowledge Transfer
Diversity and Outreach
Management Structure
Internal Management
Committee
Internal Management Committee: Responsible for day-to-day administration of the center. Monitors and facilities progress, communication, and coordination.
Internal Management
Committee

## Slide 12
Vice President for Research
Purdue University
Executive Committee
External Advisory Board
Technical Director
Szpankowski
Managing Director
Kotterman*
Technical Thrusts
Education and Human Resources Development
Knowledge Transfer
Diversity and Outreach
Management Structure
Internal Management
Committee
External Advisory Committee: Annually reviews projects; provides high-level guidance on strategic issues; provides a channel for open dialogue with the wider community
External Advisory Board

## Slide 13
Vice President for Research
Purdue University
Executive Committee
External Advisory Board
Institutional Advisory Committee
Technical Director
Szpankowski
Managing Director
Kotterman*
Technical Thrusts
Education and Human Resources Development
Knowledge Transfer
Diversity and Outreach
Coordinating Thrusts
Research, education, outreach, and knowledge transfer activities must be tightly integrated.
Thrust leads will have monthly meetings (either in person, or over video conference) to develop integrated initiatives. These meetings will include the Technical and Managing Directors.
Industry representatives from partner companies will be invited as needed.
Executive committee will minor coordination (and associated outcomes), assess coordination risks, and propose mitigation strategies

## Slide 14: Executive Committee
Composition:
  Center leadership
  Chair of the Executive Committee will not be the Director of the Center.
Coordination
  Monthly meetings conducted through telephone and/or video conference
  Senior personnel from projects and managing director will attend by invitation as needed.
  Meetings will manage new and ongoing projects; deal with issues that have arisen, and discuss possible future directions (fiscal and intellectual)
  Action items from meeting will be distributed within 24 hours.

## Slide 15: Project Management
Projects within the Center will be managed by the Executive Committee via application management, solicitation, and assessment
Managing Applications:
  Track progress of each application
  Ensure progress on towards foundational aspects
  Terminate projects no longer relevant or demonstrating insufficient progress
  Evaluate the success of collaborative investigations.
Metrics for managing applications
  Publication of quality peer-reviewed papers, software tools, and infrastructure, vis-à-vis information measures
  Collaborations between investigators exemplified by joint publications and grants
  Development of educational material that illustrate fundamental developments in the domain
  Assessment of progress reports by the peers within the Center

## Slide 16: Risk Assessment and Mitigation
Monthly meetings of executive committee will include dedicated discussion to risk assessment and mitigation strategys
Risk will be assessed on project progress, synergistic development, thrusts coordination, outreach and diversity, and knowledge transfer
  Risk assessment will be based on concrete metrics
  Mitigation strategies for at-risk areas will be developed, implemented, and monitored
  An EC member will be assigned to any at-risk area, with responsibility for monitoring mitigation, reporting progress, and making recommendations
Quarterly meetings will be held jointly between the EC and the IMC to discuss risk on all aspects of the project

## Slide 17: Internal Management Committee
Reports to the Managing Director
Monitors internal progress and communication across the Center
Committee mission:
  Resolve day-to-day issues of the center without engaging executive committee
  Raise issues that are of concern among projects, and to the user community
  Provides a forum for coordinating the many ongoing efforts, thus minimizing redundancy, and sharing success strategies
  Informs Technical Director, Executive, and Advisory Committees of larger issues that may prove problematic to the success of the project.
Research
Managing
Director
Internal
Management
Committee
Outreach
Dissemination
Education
Implementation
Applications
Projects
Projects
User
Students
Training
User Community

## Slide 18: External Advisory Board
Composition: reflects diversity of scientific domains within the Center.
  A renowned Computer Scientist who is expert in
  A renowned Information Theorist who is expert in
  Domain scientists in XXX, YYY, ZZZ.
Coordination
  External Advisory Board will receive quarterly progress reports from the Managing Director
  Will meet with the Center Director and the NSF Project Officer each year
  In-person meeting at the annual “all hands” meeting of the Center. This meeting will provide a forum for a high quality, detailed appraisal of the Center’s progress

## Slide 19: External Advisory Board: Progress Assessment
EAC will generate an annual report on the center’s progress for the Center Director and the NSF
  Will summarize assessment of the Center’s initiatives and make recommendations
Assessment and Metrics Include
  The adequacy of the synergistic development (metrics may include new collaborations, student exchanges, and interdisciplinary publications.)
  Infrastructure creation and its potential impact
  The reliability, robustness, and usability of tools and methods (metrics may user surveys, publication citations, and metrics on tool usage)
  The quality of the education and outreach component (metrics may include student surveys, diversity of program participants, statistics on outreach).
  The effectiveness of dissemination activities (metrics may include citation indices and plenary/invited talks of participants)
  Directions for Computer Science research related to Information Theory
  Recommendations for strategic recruitments
  Selection of new applications and termination of existing ones
Notes: Shankar asks for more details on the assessment tools. I’ve added some, please feel free to modify or change.

## Slide 20: Planning for Growth
Identifying Novel Directions, Selecting and Integrating New Applications:
  Recruiting: An open invitation to the entire information sciences and related applications communities
  Evaluation: By Director and Executive committee at the “All Hands” meeting, Metrics for selection will include significance/scope of the proposed application (25%), likelihood of impact (50%), and likelihood of success (25%).
  Integration: The Technical Director in consultation with the External Advisory Committee and NSF will collaborate with the PI of the new application to plan for transfer of resources to the new project.